## Slide 1: STRATEGIC PLANNING CALENDAR FOR 2018/19
Presented by Ashika Singh
7 June 2018
To be the centre of governance, providing leadership towards achieving Vision 2035.

## Slide 2
To inform departments of the Strategic Planning Calendar for the Province for 2018/19.
Purpose of Presentation
To be the centre of governance, providing leadership towards achieving Vision 2035.

## Slide 3
Strategic Planning Calendar
DATE | ACTIVITY | RESPONSIBILITY
JUNE 2018 |  | 
 | Departmental Strategic Planning Session | Department
7 June | Joint Provincial Treasury and OTP Planning Meeting | All
14 June | Joint Strategic Forum Meeting | All
21 June | Asikhulume Planning | OTP
JULY 2018 |  | 
30 July | Entities to submit their 1st draft 2019/2020 APPs to their respective Departments | Entity Managers
AUGUST 2018 |  | 
1 – 6 August | Consolidation & Editing of 1st draft 2019/20 APP | Strategic Planning Unit
10 August | SUBMISSION OF DEPARTMENTAL 1st DRAFT 2019/2020 APP TO OTP | All Departments
 | SUBMISSION OF ENTITY 1st DRAFT 2019/2020 APP with ASSESSMENT to OTP | All Departments
30 August | OTP submit DEPARTMENTAL 1st DRAFT 2019/2020 APPs and ASSESSMENTS to DPME | OTP
30 August | OTP provide feedback to Departments on Entity Assessments | OTP

## Slide 4
Strategic Planning Calendar
DATE | ACTIVITY | RESPONSIBILITY
SEPTEMBER 2018 |  | 
13 September | Joint Strategic Planning Forum | All
OCTOBER 2018 |  | 
1 - 5 October | First draft Assessments of Departments circulated to all Departments | OTP
15 October | Entities to submit their 2nd draft 2019/2020 APPs to their respective Departments | Entity Manager
25 October | Asikhulume Planning | OTP
October | Collation & assessment of 2nd draft APP inputs | Strategic Planning Units
NOVEMBER 2018 |  | 
1 – 8 November | Consolidation & Editing of 2nd draft 2019/2020 APP | Strategic Planning Unit
9 November | SUBMISSION OF 2nd DRAFT 2019/2020 APP TO OTP | All Departments
 | SUBMISSION OF ENTITY 2nd DRAFT 2019/2020 APP with ASSESSMENT to OTP | All Departments
30 November | SUBMISSION OF 2nd DRAFT 2019/2020 APP TO DPME | OTP
30 November | OTP provide feedback to Departments on Entity Assessments | OTP
DECEMBER 2018 |  | 
6 December | Joint Strategic Forum Meeting | All

## Slide 5
Strategic Planning Calendar
DATE | ACTIVITY | RESPONSIBILITY
FEBRUARY 2019 |  | 
1 – 4 February | Second draft Assessments of Departments circulated to all Departments | OTP
5 February | Entities to submit their 3rd draft 2019/2020 APPs to their respective departments | Entity Manager
11 February | SUBMISSION OF 3rd DRAFT 2019/2020 APP TO OTP | All Departments
 | SUBMISSION OF ENTITY 3rd DRAFT 2019/2020 APP with ASSESSMENT to OTP | All Departments
28 February | Third draft Assessments of Departments circulated to all Departments | OTP
 | OTP provide feedback to Departments on Entity Assessments | OTP
MARCH 2019 |  | 
1 – 5 March | 2019/2020 APPs finalised and ready for signatures | All Departments
14 March | Joint Strategic Forum Meeting | All
6-31 March | OPS plans developed and finalised | All Departments
29 March 2019 | FINAL OPS PLANS IN PLACE | 
APRIL 2019 |  | 
30 April – 30 May | FINAL adopted 2019/2020 APPs (Departments and Entities) to be submitted to OTP | All Departments

## Slide 6
Strategic Planning Team OTP
To be the centre of governance, providing leadership towards achieving Vision 2035.
Strategic Planners are available to provide departments with the necessary support and guidance as required.
  Hlengiwe Xaba: hlengiwe.xaba@kznpremier.gov.za: 0635021949
  Lindinjabulo Hlubi: linda.hlubi@kznpremier.gov.za: 0635021947
  Ashika Singh: ashika.singh@kznpremier.gov.za: 0786574207

## Slide 7
Dates to be Remembered
To be the Centre of governance, providing leadership towards achieving Vision 2035.
 | 10th August 2018: | First draft APP due
 | 9th November 2018: | Second draft APP due
 | 11th February 2019: | Third draft APP due

## Slide 8
Programme Implementation Planning is currently a pilot standard for MPAT and KZN is not doing well.
Whilst the Guidelines are undergoing refinement, some best practice and sound tools are suggested in the guidelines that could enhance our programme design, as well as monitoring and evaluation of our programmes.
Some of the generic challenges observed during the MPAT process include the following:
  • Departments are using their annual performance plans as evidence, which is not the same as a programme implementation plan.
  • Poor diagnostics and/or not outlining cost benefit analysis (financial and/or nonfinancial) and option analysis motivation.
  • “Theory of Change” not clearly articulated and/or mapped
  • Risk Management not addressed.
  • Budget over the MTEF not indicated.
  • Poor or no lifecycle monitoring and evaluation plan.
Programme Implementation Planning

## Slide 9
Whilst we have engaged the DPME on the refinements, we are negotiating the standard and hope to get feedback in due course. In the mean time we encourage all involved in the planning, design, implementation and monitoring of evaluation of programmes to familiarise themselves with the guidelines (DPME Guideline 2.2.3 Guideline for the planning implementation programmes Created 30 July 2013 Updated 19 September 2014).
These can be obtained from the DPME website under the Evaluations Repository:
https://evaluations.dpme.gov.za/images/gallery/Guideline%202.2.3%20Implementation%20%20Programmes%2013%2007%2030.pdf
Programme Implementation Planning
To be the centre of governance, providing leadership towards achieving Vision 2035.

## Slide 10
Thank You
To be the centre of governance, providing leadership towards achieving Vision 2035.